## df (hidden)
ProjectNumber | Project Name | Leader | Project Status | Field Work Complete | Lab Analysis Complete | Planned Field | Actual Field | Planned Report | Actual Report
0 | 0 | 0 | 0 | 0 | 0 | 2018-07-09 | 0 | 2018-10-01 | 0

## Project Update
Project Number
Project Name
Leader
Project Status
Field Work Complete
Lab Analysis Complete
Notes
Planned Field Start | 2018-07-09
Field Days | 5
Lab Turnaround | 35
Pre Planning Stages | Actual Date | Due Date | Milestone Status
Draft QAPP |  | 2018-06-18 | OVERDUE
QAPP Technical Review |  | 2018-06-25 | OVERDUE
QAPP Final |  | 2018-07-02 | OVERDUE
Field Start |  | 2018-07-09 | OVERDUE
Fied End |  | 2018-07-14 | OVERDUE
Lab Reported |  | 2018-08-18 | OVERDUE
Tech Review |  | 2018-09-24 | OVERDUE
Report Finalized |  | 2018-10-01 | OVERDUE
File Complete |  | 2018-10-16 | OVERDUE
Formulas:
Due Date = [Due Date, row above]+B11
Due Date = [Due Date, row above]+35+2
Milestone Status = IF([Actual Date]="",IF([Due Date]>TODAY(),"on schedule","OVERDUE"),IF([Actual Date]<=[Due Date],"Completed ","LATE Completion"))

## tables (hidden)
project | field work | Ecology |  | 2018-11-26 | status
status | status | Ackerman | 412
Confirmed | Yes | Barlet | 414
Completed | No | Dorn | 409
Hold | Delayed | Dye | 411
Cancelled |  | Flexner | 405
Pushed to Next Year |  | Kalla | 404
Conditional |  | Little | 407
Declined |  | McMahan | 410
|  | Parsons | 406
|  | Ruiz | 413
|  | White | 408